## GANTT
CA PROJECT METHODOLOGY |  | Phase |  | PLAN | [5 empty] | DESIGN |  |  |  |  | BUILD | [10 empty] | RELEASE
Lofthus fukt og saft - Web site |  | Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
GANTT Chart |  | Week |  | PLAN 1: 1; PLAN 6: 2; DESIGN 11: 3; BUILD 16: 4; BUILD 21: 5
Responsible for task | Task | Start | End
Project Manager | Project Management | 1 | 25
Project Manager | Customer Contact | 1 | 25
Project Manager | Kick-off meeting 1 | 1 | 1
Project Manager | Goals | 1 | 2
Project Manager | Need | 1 | 2
Project Manager | Kick-off meeting 2 | 3 | 3
Project Manager | Proposal | 3 | 3
Project Manager | Contract | 3 | 3
Project Manager | Project Planning | 3 | 4
Designer 1 | Research | 4 | 5
Copywriter | Content Planning | 5 | 6
Designer 2 | Site Outline | 5 | 5
Designer 1 | Site Structure | 6 | 7
Designer 2 | Moodboard | 7 | 7
Designer 1 | Style Tile | 8 | 8
Designer 2 | Wireframes | 9 | 9
Designer 1 | UX/UI planning | 9 | 10
Designer 2 | Hi-fidelity mockup | 10 | 11
Developer 1 | Coding, Integration and Site Build | 12 | 22
Developer 2 | UX/UI testing | 16 | 22
Copywriter | Copy Writing - Sales | 7 | 9
Copywriter | Copy Writing - Brand | 10 | 12
Copywriter | Copy Writing - History | 13 | 14
Photographer | Photoshoot - brand | 7 | 11
Photographer | Photoshoot - products | 12 | 14
Photographer | Photoshoot - employee | 15 | 16
Developer 2 | Cross Platform and Browser Testing | 23 | 24
Developer 1 | Validation | 23 | 23
Developer 1 | Refinement | 24 | 24
Project Manager | Handover | 25 | 25
Developer 2 | Launch | 25 | 25 | bar: RELEASE 25

## TASKS
Task | Duration | Finished
Project Management | 20 | FALSE
Customer Contact | 20 | FALSE
Kick-off meeting 1 | 1 | FALSE
Goals | 2 | FALSE
Need | 2 | FALSE
Kick-off meeting 2 | 1 | FALSE
Proposal | 1 | FALSE
Contract | 1 | FALSE
Project Planning | 2 | FALSE
Research | 2 | FALSE
Content Planning | 2 | FALSE
Site Outline | 1 | FALSE
Site Structure | 2 | FALSE
Moodboard | 1 | FALSE
Style Tile | 1 | FALSE
Copy Writing - Sales | 3 | FALSE
Copy Writing - Brand | 3 | FALSE
Copy Writing - History | 2 | FALSE
Photoshoot - brand | 5 | FALSE
Photoshoot - products | 3 | FALSE
Photoshoot - employee | 2 | FALSE
Wireframes | 1 | FALSE
UX/UI planning | 2 | FALSE
Hi-fidelity mockup | 2 | FALSE
Coding, Integration and Site Build | 10 | FALSE
UX/UI testing | 5 | FALSE
Cross Platform and Browser Testing | 2 | FALSE
Validation | 1 | FALSE
Refinement | 1 | FALSE
Handover | 1 | FALSE
Launch | 1 | FALSE

## CONTRIBUTORS
Contributor | Role
Project Manager | Project Manager
Copywriter | Copywriter
Designer 1 | Designer 1
Designer 2 | Designer 2
Developer 1 | Developer 1
Developer 2 | Developer 2
Photographer | Photographer